## Introduction
Initiative Type | Business Excellence / Growth / Business Transformation/Digitalisation etc
Project Title | {enter name of business initiative}
Program Manager
Project Manager
Test Team
Training Team
Date Commenced

## Instructions
INSTRUCTIONS / GUIDANCE | Updated December 2021
The tasks listed in the template are indicative of the tasks you might need to include in your initiative.
You can delete ones which don't apply and add in more rows as required
The Plan phase kicks off after Define but for completeness the Define phase is included in the template
You will need to work with IT, training, testing and other stakeholders such as Finance and HR team to determine the tasks and appropriate durations to allow for each considering the resource availability, holidays, blackout periods ( WE NEED TO TAILOR THIS TO THE SOCIETY), Christmas, etc.
It can be good to look at other project plans to get inspiration re the tasks they included and the durations planned v actual and commentary as to why there were delays if any
Build in contingency to your dates to allow for unexpected spikes in people's day jobs, bugs found during testing, etc.
Review your dates and progress regularly, updating the Status, RAG, % Complete, Latest forecast completion date and Actual Completion dates and comments fields

## Example Project Plan (hidden)
Project Cycle Phases | BU | Person Responsible | Task | Status (Not Started / In Progress / Blocked / Complete) | RAG (red / amber or green) | Start Date | Planned completion Date | % Complete | Latest forecast completion date | Actual completion | Variance | Comment (e.g reason for variance / Red or Amber status etc)
Define
Define | Property | Noreen Gillane | Gather requirements & discuss at team meeting | Not Started |  |  | 2021-04-01 |  | 2021-04-05 |  | 4
Define | Property | Noreen Gillane | Document requirements on Business Requirement Document template | [7 empty] | 0
| Property | Project Manager | Consider whether Finance/Compliance or other BU needs to be involved & liaise
Define | Property | Noreen Gillane | Send BRD to BU Lead - Conor Holland |  | Green | [5 empty] | 0
Define | Property | Noreen Gillane | Update BRD post feedback from BU lead and stakeholders | [7 empty] | 0
Define | Property | Conor Holland | Sign-off Requirements | [7 empty] | 0
Define | Property | Noreen Gillane | Send to Sinead Cosgrave for review | [7 empty] | 0
Define | Shared Services | Sinead Cosgrave | Review & discuss / clarify | [7 empty] | 0
Define | Shared Services | Sinead Cosgrave | Send to IT Team for review and feedback | [7 empty] | 0
Define | [10 empty] | 0
Plan
Plan | IT | John Healy | Understand key differences in business requirements & advise Sinead | Not Started | [6 empty] | 0
Plan | IT | John Healy | Understand scope - resources & budget requirements | [7 empty] | 0
Plan | Shared Services | Sinead Cosgrave | Revert to the business with key issues/ | [7 empty] | 0
Plan | Shared Services | [9 empty] | 0
Plan | Property | Noreen Gillane | Document Comms and Training plan to support launch | [7 empty] | 0
Plan | [10 empty] | 0
Plan | [10 empty] | 0
Plan | [10 empty] | 0
Build
| IT | John Healy | Oversee solution implementation | Not Started | [6 empty] | 0
Build | IT | Michael Gallagher | Make amendments to current built infrastructure to adapt to differences | [7 empty] | 0
Build | IT | Russ Holmes | Add required fields to core system- Elite | [7 empty] | 0
Build | IT | Pascal Tuohy | Implement new fields/flags in MI | [7 empty] | 0
Build | IT | Ed Ball | Turn On/Off functionality in Software as per business requirements | [7 empty] | 0
Build | IT | John Healy | Revert to business with issues/ problems | [7 empty] | 0
Build | Property | Noreen Gillane | Develop training materials to train testers / to train team for launch | [7 empty] | 0
Build | Property | Joanne Stynes | Document test scenarios for Test team including regression testing. Create test data if reqd | [7 empty] | 0
Build | Property | Joanne Stynes | Prepare test team for upcoming test phase | [7 empty] | 0
Test & Train
Test & Train | IT | Test | Complete system test | Not Started | [6 empty] | 0
Test & Train | Property | Test Team | Complete User testing & feedback sheet for IT | [7 empty] | 0
Test & Train | Property | User Test feedback | Send to business for user testing | [7 empty] | 0
Test & Train | IT | Russ Holmes | Amend/enhance/fix bugs and issues raised by user testing | Not Started | [6 empty] | 0
Test & Train | Property | Test Team | retest amended items | [7 empty] | 0
Test & Train | Property |  | Finalise training materials (updated screen shots etc) | [7 empty] | 0
Test & Train | Property | Noreen Gillane | Sign off on Go NO Go | [7 empty] | 0
Test & Train | Property |  | Agree Super user/Champion | [7 empty] | 0
Test & Train | Property |  | Train team on new functionality | [7 empty] | 0
Test & Train | Property | Noreen Gillane | Communicate Go Live | [7 empty] | 0
Launch
| IT | John Healy | Go Live with new change at weekend/overnight | Not Started | [6 empty] | 0
| IT | Russ Holmes | Test system is Live and working - liaise with test team | Not Started | [6 empty] | 0
| IT | Noreen Gillane | Communicate Go Live | Not Started | [6 empty] | 0
| IT | Champion/Superuser | Gather Go Live issues list | Not Started | [6 empty] | 0
| IT | Russ Holmes | Fix Go Live Issues/ enhance where required | Not Started | [6 empty] | 0
| IT | Champion/Superuser | Gather Go Live enhancements | Not Started | [6 empty] | 0
0
0
0
0
0
0
0
0
0

## definitions
INITIATIVE TYPE | This should map back to Vision & Growth Plan Initiatives or Business As Usual (BAU)
Project Phase | This field is used to indicate where the initiative is in the project life cycle. 6 phases have been defined
Define | Business requirements definition phase will document the problem or issue that needs to be resolved and the functionality required to solve it. The document should include a section for Assumptions, Dependencies, Issues and Risks which will be refined as the project proceeds. The BRD (business requirements document) will be signed off by the Business Stakeholders and handed over to IT or other department responsible so they can assess the options at the end of this phase
Plan | IT/Department provide initial feedback and ask clarifying questions to determine how much effort is required. They will document the system changes if any via a Functional Specification. Project Manager collaborates with IT and business to finalise the project plan (in effect this will baseline the plan with resources committed to deliver it) taking into consideration all the business, reporting and system activities required to implement the change including training and communications.
Build | During this phase IT are developing the solution or if not an IT based initiative the core business team are developing the To Be model / process / report etc
Test & Train | There are 2 components to test - system test conducted by the IT dept and then User Acceptance Testing performed by the business to ensure that the solution will meet their needs for multiple scenarios. Business SMEs will need to define test scenarios and write / execute user acceptance test scripts. In parallel Business document the updated processes / work instructions and any controls. Rollout plan to be finalised Business train the users and communicate to Members if any impact To exit this phase the Go / No Go checklist will be signed off by the business stakeholders and IT
Launch | IT deploy changes in production / Program Manager launches new process Program manager & SMEs / IT support users through open office hours (calls) / specific help alias with any teething issues Retire any old systems / processes if appropriate.
Maintain / Enhance | After launch and the initial post go-live support period, the standard Change Request Process will manage any further enhancements
RAG: | This is a quick visual way to indicate if the initiative is on track or not using a simple traffic light system. Please select the appropriate colour from the drop down and colour code the cell also.
On track, no risk to successful completion
Minor slippage or potential risk of slipping timeline, budget or resources. Mgmt intervention may be reqd to ensure back on track
Slipped / Significant risk of slipping, corrective action required
GO LIVE DATE
PLANNED | This is the initial planned go live date agreed during the Plan phase. The column has been formatted to display the date format dd-mmm-yy but you can enter as dd/mm/yy and it will auto-correct
Latest Forecast | This is the CURRENT FORECASTED planned go live date which should be updated at least monthly for the SMT or ideally weekly for the project team meetings / status updates. Initially it will be the same as the planned go live date but may slip over time.
Variance (days) | This is set to auto-calculate the number of days (if any) between the planned and latest forecasted date. Ex: Planned Jan 1st, actual Feb 1st will show a variance of 31 days.

## Example of Planner
Project Phases | BU | Person Responsible | Task | Status (Not Started / In Progress / Blocked / Complete) | RAG (red / amber or green) | Start Date | Planned completion Date | % Complete | Latest forecast completion date | Actual completion | Variance | Comment (e.g reason for variance / Red or Amber status etc)
Define
Define | Casualty | X | Gather requirements & discuss with SMEs | Complete | Green | 2021-02-25 | 2021-04-01 | 100% | 2021-04-05 |  | 4
Define | Casualty | X | Document requirements using Business Requirement Document template | Complete | Green | 2021-03-04 | 2021-03-18 | 100% | 2021-03-20 |  | 2
Define | Casualty | X | Consider whether Finance/Compliance or other BU needs to be involved & engage as reqd | Complete | Green | 2021-03-18 | 2021-03-23 | 100% | 2021-03-30 |  | 7
Define | Casualty | X | Obtain input from SMEs via a survey to Adjusters | Complete | Green | 2021-03-11 | 2021-03-25 |  | 2021-03-25 |  | 0
Define | Casualty | X | Send BRD to BU Leads - | Complete | Green | 2021-03-25 | 2021-03-30 | 100% | 2021-03-31 |  | 1
Define | Casualty | X | Update BRD post feedback from BU lead and stakeholders | Complete | Green | 2021-03-30 | 2021-04-04 | 100% | 2021-04-05 |  | 1
Define | Casualty | X | Schedule sign-off meeting | Complete | Green | 2021-04-04 | 2021-04-04 |  | 2021-04-05 |  | 1
Define | Casualty | X | Send out BRD as a pre-read | Complete | Green | 2021-04-06 | 2021-04-06 |  | 2021-04-06 |  | 0
Define | Casualty | X | Sign-off Requirements | Complete | Green | 2021-04-08 | 2021-04-08 | 100% | 2021-04-08 | 2021-04-08 | 0
Define | Casualty | X | Send to for review | Complete | Green | 2021-04-09 | 2021-04-09 | 100% | 2021-04-09 | 2021-04-09 | 0
Define | Shared Services | Y | Review & discuss / clarify | Complete | Green | 2021-04-10 | 2021-04-10 | 100% | 2021-04-10 | 2021-04-10 | 0
Define | Shared Services | Y | Send to IT Team for review and feedback | Complete | Green | 2021-04-12 | 2021-04-12 | 100% | 2021-04-12 | 2021-04-12 | 0
Plan
Plan | IT | R | Understand key differences in business requirements & advise | InProgress | Green | 2021-04-12 | 2021-04-21 |  | 2021-04-26 |  | 5
Plan | IT | R | Understand scope - resources & budget requirements | InProgress | Green | 2021-04-12 | 2021-04-21 |  | 2021-04-26 |  | 5
Plan | Shared Services | Y | Revert to the business with key issues | InProgress | Green | 2021-04-21 | 2021-04-26 | 50% | 2021-04-26 |  | 0
Plan | IT | R | Finalise approach and dates for IT efforts | Not Started | Amber | 2021-04-26 | 2021-04-30 |  | 2021-04-26 |  | -4
Plan | Casualty | X | Document Comms and Training plan to support launch | InProgress | Green | 2021-04-21 | 2021-04-26 |  | 2021-04-26 |  | 0
Plan | Casualty | X | Identify test resources and confirm availability | InProgress | Green | 2021-04-21 | 2021-04-26 |  | 2021-04-26 |  | 0
Plan | Casualty | X | Incorporate input from IT, Training & Operations to finalise plan | InProgress | Amber | 2021-04-26 | 2021-04-27 |  | 2021-04-29 |  | 2
Plan | Casualty | X | Obtain approval to plan with commitment to provide required resources and agree to move to BUILD | Not Started | Not Started | [5 empty] | 0
Build
Build | IT | R | Oversee solution implementation | Not Started | [6 empty] | 0
Build | IT | R | Make amendments to current infrastructure (Call Collect upgrade server and access excl VPN so can drop VOA) | Not Started | [6 empty] | 0
Build | IT | R | Add required fields to core system- Elite | Not Started | [6 empty] | 0
Build | IT | R | Call Collect updates and enhancements | Not Started | [6 empty] | 0
Build | IT | R | Revert to business with issues/ problems | Not Started | [6 empty] | 0
Build | Casualty | X | Develop training materials to train testers | Not Started | [6 empty] | 0
Build | Casualty | X | Document test scenarios for Test team including regression testing. Create detailed test scripts | Not Started | [6 empty] | 0
Build | Casualty | X | Create test data if reqd | Not Started
Build | Casualty | X | Finalise training materials to train team pre-launch | Not Started
Build | Casualty | X | Prepare test team for upcoming test phase | Not Started | [6 empty] | 0
Test & Train
Test & Train | IT | R | Complete system test (in Dev & Test environments) and confirm to Business to start user testing | Not Started | [6 empty] | 0
Test & Train | Casualty | X | Execute User testing & update issue tracker for IT (bugs / enhancements) | Not Started | [6 empty] | 0
Test & Train | IT | R | Amend/enhance/fix bugs and issues raised by user testing | Not Started | [6 empty] | 0
Test & Train | Casualty | X | Retest amended/fixed items | Not Started | [6 empty] | 0
Test & Train | Casualty | X | Complete end to end testing and regression testing | Not Started
Test & Train | Casualty | X | Finalise training materials (updated screen shots etc) if required | Not Started | [6 empty] | 0
Test & Train | Casualty | X | Update the Go / No Go with latest status and schedule meeting to review | Not Started
Test & Train | Casualty | X | Management sign off on Go / No Go criteria with approval to proceed to LAUNCH | Not Started | [6 empty] | 0
Test & Train | Casualty | X | Agree Super user / Champion to support team through launch | Not Started | [6 empty] | 0
Test & Train | Casualty | X | Train team on new functionality | Not Started | [6 empty] | 0
Test & Train | IT | R | Document new / changes to Tool / Technology | Not Started
Test & Train | IT | R | train the Level 1 & 2 support team on the new technology. | Not Started
Test & Train | IT | R | Handover application from development team to Helpdesk | Not Started
Test & Train | Casualty | X | Communicate Go Live date & support model | Not Started | [6 empty] | 0
Launch
Launch | IT | R | Go Live with new change at weekend/overnight | Not Started | [6 empty] | 0
Launch | IT | R | Test system is Live and working - liaise with test team | Not Started | [6 empty] | 0
Launch | IT | R | Implement new fields/flags in LEI for MI | Not Started
Launch | Casualty | X | Communicate Go Live | Not Started | [6 empty] | 0
Launch | IT | R | Gather Go Live issues list | Not Started | [6 empty] | 0
Launch | IT | R | Fix Go Live Issues/ enhance where required | Not Started | [6 empty] | 0
Launch | Casualty | X | Gather Go Live enhancements | Not Started | [6 empty] | 0
Launch | Casualty | X | Conduct review (lessons learnt for future initiatives) | Not Started | [6 empty] | 0
0
| 1. document new technology and 2. train the Level 1 & 2 support team on the new technology. 3. Handover application from development team to Helpdesk | [9 empty] | 0
0
0
0
0
0
Formulas:
Planned completion Date = [Start Date]+14
Planned completion Date = [Start Date]
Start Date = [Planned completion Date, row above]
Start Date = [Start Date, row below]-2
Latest forecast completion date = [Latest forecast completion date, row above]+1
Actual completion = [Actual completion, row above]+1

## drop down values (hidden)
RAG Status | Project Status
Green | Not Started
Amber | InProgress
Red | Blocked
TBC | Complete
Not Started
N/A